## Recipes
Recipe Name | Recipe Type | Number | Operation name | Precedence | Subcontractor | Crew Type | Min. Crews Required | Max. Crews Required | Equipment type | Qty. Equipment Required | Crane type | Material | Action | Qty. Material Required | Production rate | ALICE duration (hours)
Grade Beams | Construction | 1 | Backfill to Top of Cap | 6FS |  | Foundation Laborer Crew | 1 | 1 | Excavator | 1 | [5 empty] | 2*8
Grade Beams | Construction | 2 | Excavate | ^FS |  | Foundation Excavator Operator | 1 | 1 | Excavator | 1 | [5 empty] | 2*8
Grade Beams | Construction | 3 | Layout | 2FS,$FS |  | Layout Crew | 1 | 1 | [7 empty] | 8*1
Grade Beams | Construction | 4 | Place Ftg Forms | 3FS |  | Foundation Carpenter Crew | 1 | 1 | [7 empty] | 4*8
Grade Beams | Construction | 5 | Install Rebar for Piles Caps & Grade Beams | 4SS+48.0,3FS |  | Foundation Rebar Crew | 1 | 1 | [7 empty] | 3*8
Grade Beams | Construction | 6 | Strip Forms | 10FS |  | Foundation Laborer Crew | 1 | 1 | [7 empty] | 1*8
Grade Beams | Construction | 7 | UG Plumbing Installation | 3FS |  | Plumbing Underground | 1 | 1 | [7 empty] | 5*8
Grade Beams | Construction | 8 | UG Mechanical Installation | 3FS |  | Mechanical Underground | 1 | 1 | [7 empty] | 5*8
Grade Beams | Construction | 9 | UG Electrical Installation | 3FS |  | Electrical Underground | 1 | 1 | [7 empty] | 5*8
Grade Beams | Construction | 10 | Pile Caps & Grade Beams Pour | 4FS,7FS,5FS,9FS,8FS |  | Foundation Pour Crew | 1 | 1 | [7 empty] | 1*8
Grade Beams | Construction | 11 | Finish Top of Footing | 10SaS+1.0 |  | Foundation Mason Finish Crew | 1 | 1 | [7 empty] | 8

## Resource pool
Subcontractor | Trade | Crew | Qty. Available | $/ hour | #people/crew | Equipment | Qty. Available | $/ hour | Cranes | Radius (ft) | Move time (hrs) | Qty. Available | $/ hour | Material | Type | Qty. Available | $/ unit | Production rate | Qty/hr
| Mechanical | Mechanical Underground | 1 | 500 | 5 | Excavator | 1 | 40
| Reinforcing Steel | Foundation Rebar Crew | 1 | 500 | 5
| Plumbing | Plumbing Underground | 1 | 500 | 5
| Electrical | Electrical Underground | 1 | 500 | 5
| Concrete | Foundation Carpenter Crew | 2 | 1000 | 10
| Concrete | Foundation Excavator Operator | 1 | 100 | 1
| Concrete | Foundation Laborer Crew | 1 | 2000 | 20
| Concrete | Foundation Mason Finish Crew | 1 | 2000 | 20
| Concrete | Foundation Pour Crew | 2 | 2000 | 20
| Concrete | Layout Crew | 2 | 200 | 2